## Product Backlog
Product Name: | ELSA | [6 empty] | Complete Fields in Green!!!
Team ID: | KILI
| Team Member Name | [5 empty] | Initials | Student ID
Required | Nebojsa Kilibarda | [5 empty] | NK | 1001934192
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 24 |  |  |  | Total | Total number of features (in column H)
1 | 19 | 5 |  |  | 1 | Total features left at the end of Sprint #1
2 | 13 | 6 |  |  | 2 | Total features left at the end of Sprint #2
3 | 8 | 5 |  |  | 3 | ...and so on
4 | 4 | 4
5 | 0 | 4
Note: Priority and specs for unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
[5 empty] | Sprint to which Feature is Assigned |  |  | Features
Feature ID | Priority | Required | Bonus | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CUST | 1 | 1 |  | 3 | 1 | Finished in Sprint 1 | Sales Staff | Remember each customer’s name and contact info | Ship them products repeatedly | Validate the email address (lightly)
OPT | 2 | 1 |  | 3 | 1 | Finished in Sprint 1 | Inventory | Maintain a list of options for a desktop (e.g., disk, RAM, CPU) | Select them when designing a new desktop product | Validate that the cost is not negative
DESKT | 3 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Define a new desktop configuration from options | Can quickly customize products for my customers
ORDER | 4 | 1 |  | 8 | 1 | Finished in Sprint 1 | Sales Staff | Associate a customer with one or more desktops into an order | Keep track of who has bought what
STORE | 5 | 1 |  | 13 | 1 | Finished in Sprint 1 | Sales Staff | Provide a central collection of the above data | Create and manage information to run my store efficiently
WIN | 6 | 2 |  | 13 | 2 | Finished in Sprint 2 | Sales Staff | Add a GUI main window with menubar | Use it more easily | Recommend baselining Nim from Lecture 12
INSCU | 7 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | Insert new Customers via a sequence of dialogs | Do everything within the GUI | Recommend JOptionDialog from Lecture 13
INSOP | 8 | 2 |  | 3 | 2 | Finished in Sprint 2 | Sales Staff | Insert new Options via a sequence of dialogs | Do everything within the GUI
INSCO | 9 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | Insert new Computers via a sequence of dialogs | Do everything within the GUI
DISP | 10 | 2 |  | 5 | 2 | Finished in Sprint 2 | Sales Staff | List data (customers, options, and computers separately) in the main window display | Access the data directly in the window | You’ll need a View menu for this, and perhaps a JLabel in the main window center section
TOOLB | 11 | 2 |  | 8 | 2 | Finished in Sprint 3 | Sales Staff | Add a simple toolbar to the main window | Use the app with pushbutton convenience | Part of the Nim baseline. Create your own icons or find some online.
ABOUT | 12 | 3 |  | 2 | 2 | Finished in Sprint 2 | Director | (If needed) Provide a simple text-only About dialog | Avolid a lawsuit | (If needed) Rewrite the text from Nim's implementation to comply with toolbar icon license obligations
ABOSK | 13 | 3 |  | 5 | 3 | In Work | Director | Provide About dialog with sketch as or around a bitmap logo for aesthetics and documenting licenses | Impress users | Recommend a subclass of JPanel from Lecture 15 with a simple diagram plus Jlabels in one or more JPanels with program information
SAVE | 14 | 3 |  | 13 | 3 | Finished in Sprint 3 | Manager | Save the data to a default file (File > Save) | Persist our data through the years | This requires modifying the “model” to save (via method) and reload (via constructor) each object from a provided stream
NEW | 15 | 3 |  | 1 | 3 | Finished in Sprint 3 | Manager | Create a new, empty store | Start new franchises | This is as easy as “new Store” with a name
SAVAS | 16 | 3 |  | 5 | 3 | Finished in Sprint 3 | Manager | Save the data to a specified file (File > Save As) | Persist our data through the years | Use JfileChooser
LOAD | 17 | 3 |  | 8 | 3 | Finished in Sprint 3 | Manager | Load the data from a specified file (File > Open) | Persist our data through the years | Use JfileChooser
INSOR | 18 | 4 |  | 5 | 4 | Finished in Sprint 4 | Sales Staff | Insert new Orders via a sequence of dialogs | Do everything within the GUI
OCOST | 19 | 4 |  | 5 | 4 | Finished in Sprint 4 | Sales Staff | Calculate and display total cost of order | Know how much to charge the customer
DISP2 | 20 | 4 |  | 2 | 4 | Finished in Sprint 4 | Sales Staff | List ORDERS in the main window display | Access the order data | This is a minor change
DCUST | 21 | 4 |  | 13 | 4 | Finished in Sprint 4 | Sales Staff | Replace sequencial dialogs with custom dialogs | Enter data more quickly | More practice with custom dialogs (just Insert Customer & Option here) - INCLUDE icon used on button in the dialog
UNIQ | 22 | 5 |  | 8 | 5 | Finished in Sprint 5 | Manager | Avoid duplicate data entry | Keep the database clean | Use a HashSet for Store Lists with valid hashCode implementations for the 4 store data classes
SORT | 23 | 5 |  | 5 | 5 | Finished in Sprint 5 | Sales Staff | Sort customer names | Find customers more quickly | Use a TreeSet for the Customer list in Store
GSAVE | 24 | 5 |  | 13 | 5 | Finished in Sprint 5 | Director | Reduce lines of code | Save money on maintenance contracts | Use a generic save method for all Lists in the Store
BONUS WORK – COMPLETE ABOVE FEATURES FIRST!!!
SCROL |  |  | 10 | 5 |  |  | Customer | Make the main window’s data area scrollable | See large volumes of data | The exact settings (e.g., are the scrollbars always visible or only when scrolling is available?) are up to you
DEPR |  |  | 25 | 13 |  |  | Inventory | Deprecate a product | Avoid selling products that are out of production | This requires a Boolean with getter and setter in the Options and Desktop classes to indicate which are deprecated. The index number may pose interesting challenges, since deprecation will create gaps.
SBAR |  |  | 15 | 8 |  |  | Manager | Add a status bar to the main window | Better track status of messages | A stack of messages that can be reviewed would be worth more!
DTAIL |  |  | 40 | 21 |  |  | Customer | Provide a detail view of a product type info in the main window, including a picture | Provide additional info about each product | The image can be a file. Store the filename in Option, and load from disk when required
SPEC |  |  | 25 | 13 |  |  | Customer | Store and display type-specific data | Ensure I purchase the correct product | Use inheritance with polymorphism

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2023-02-21 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-02-28
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 17
Day 1 Left | 15 | 2
Day 2 Left | 0 | 15
Day 3 Left | 0 | 0
Day 4 Left | 0 | 0
Day 5 Left | 0 | 0
Day 6 Left | 0 | 0
Day 7 Left | 0 | 0
Task ID | Feature ID | Assigned To | Task | Status | Notes
1 | CUST | NK | Write Customer class | Completed Day 1
2 | CUST | NK | Add xml.build file to P05 | Completed Day 1
3 | CUST | NK | Write Regression CustomerTest.java | Completed Day 2
4 | CUST | NK | add to github | Completed Day 2
5 |  | NK
6 | OPT | NK | Write Option Class | Completed Day 2
7 | OPT | NK | Consult with Prof.Rice on implementation of cost() | Completed Day 2
8 | OPT | NK | Test Run with TestStore.java | Completed Day 2
9 | OPT | NK | add to github | Completed Day 2
10 |  | NK
11 | ORDER | NK | Write Order class | Completed Day 2
12 | ORDER | NK | Test Run with TestStore.java | Completed Day 2
13 | ORDER | NK | Write OrderTest.java regression test | Completed Day 2
14 |  | NK
15 | DESKT | NK | create Computer.java class | Completed Day 2
16 | DESKT | NK | Test using TestStore.java | Completed Day 2
17 | DESKT | NK | Add to github | Completed Day 2
18 |  | NK
19 | STORE | NK | Git pull and copy to P05 | Completed Day 2
20 | STORE | NK | Test with TestStore.java | Completed Day 2
21 | STORE | NK | Add to github | Completed Day 2
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2023-02-28 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-03-07
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 21
Day 1 Left | 21 | 0
Day 2 Left | 21 | 0
Day 3 Left | 21 | 0
Day 4 Left | 15 | 6
Day 5 Left | 10 | 5
Day 6 Left | 10 | 0
Day 7 Left | 3 | 7
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | WIN |  | Copy P05 dir to P06 | Completed Day 4
2 | WIN |  | Handle file discrepancies and set up packages | Completed Day 4
3 | WIN |  | Create main win and menubar items | Completed Day 4
4 | WIN |  | Add empty listeners | Completed Day 4
5
6 | INSCU |  | Create JOptionPane to take two separate strings | Completed Day 4
7 | INSCU |  | Unify the two strings using gridLayout | Completed Day 5
8 |  |  | Create try/catch clause and handle cancel input | Completed Day 5
9
10 | INSOP |  | Create JOptionPane with string and double input | Completed Day 4
11 | INSOP |  | Add instance of option created to store | Completed Day 5
12
13 | INSCO |  | Recreate JoptionPane based on Customer | Completed Day 5
14 | INSCO |  | Create a JComboBox for options | Completed Day 5
15 | INSCO |  | Import options from store and ensure proper functionality | Completed Day 7
16
17 | DISP |  | Display requested information in the main window | In Work
18 | DISP |  | Write code that adds options to computer | In Work
19 | DISP |  | Erase extra code and comments | Completed Day 7
20
21 | TOOLB |  | Create 6 buttons based on 'Nim' | Completed Day 7
22 | TOOLB |  | Insert icons and other fields to Jtoolbar | Completed Day 7
23 | TOOLB |  | display contents in main win after a button is pushed (currently separate win) | In Work
24
25 | ABOUT |  | Attribute artists for their icons | Completed Day 7
26 | ABOUT |  | Make sure the code is clean and uniform | Completed Day 7
27 | ABOUT |  | Write comments for the code used | Completed Day 7
28 | ABOUT
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2023-03-07 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-03-21
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 11
Day 1 Left | 11 | 0
Day 2 Left | 11 | 0
Day 3 Left | 11 | 0
Day 4 Left | 11 | 0
Day 5 Left | 11 | 0
Day 6 Left | 11 | 0
Day 7 Left | 1 | 10
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SAVE |  | Add write/read functionality to store and its members | Completed Day 7
2 | SAVE |  | Implement onSaveClick method using BufferedWriter | Completed Day 7
3 | SAVE |  | Create Jbutton and JMenuItem for 'Save' | Completed Day 7
4
5 | NEW |  | Write simple onNewClick method that instances another store | Completed Day 7
6 | NEW |  | Add JButton and JMenuItem that corresponds with 'New' | Completed Day 7
7
8 | SAVAS |  | Implement onSaveAsClick w/ JFileChooser | Completed Day 7
9 | SAVAS |  | Add Jbutton and JMenuItem for SaveAs | Completed Day 7
10
11 | LOAD |  | Implement onOpenClick method using JFileChooser | Completed Day 7
12 | LOAD |  | Add a Jbutton and JMenuItem for 'Open' | Completed Day 7
13
14 | ABOSK |  | Create personalized icon for the about dialog | In Work
15 | ABOSK |  | Add credits for new icons used for Open, Save, Save As, New | Completed Day 7
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2023-04-11 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-04-18
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 6
Day 1 Left | 6 | 0
Day 2 Left | 6 | 0
Day 3 Left | 6 | 0
Day 4 Left | 6 | 0
Day 5 Left | 6 | 0
Day 6 Left | 6 | 0
Day 7 Left | 0 | 6
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | DISP |  | Redesign ELSA visually by chaning all of the icons | Completed Day 7
2 | DCUST |  | Add Icons to the unified dialogs | Completed Day 7
3 | OCOST |  | Create a cost function and bring Class Order up to date | Completed Day 7
4 | ABOUT |  | Update the About page | Completed Day 7
5 | DISP2 |  | List Orders in Main Win | Completed Day 7
6 | INSOR |  | Create a sequence of dialogs to ease the process of taking orders | Completed Day 7
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2023-04-18 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-04-25
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 4
Day 1 Left | 4 | 0
Day 2 Left | 4 | 0
Day 3 Left | 4 | 0
Day 4 Left | 4 | 0
Day 5 Left | 4 | 0
Day 6 Left | 4 | 0
Day 7 Left | 0 | 4
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | SORT |  | Implement a TreeSet with comparable interface to sort customers by name, email | Completed Day 7
2 | GSAVE |  | Write a Saveable interface with abstract method save | Completed Day 7
3 | GSAVE |  | Rewrite the save() method to a generic method and change dependant code | Completed Day 7
4 | UNIQ |  | Override the hashCode() method for each class | Completed Day 7
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint # | 6 | BONUS | Complete Fields in Green!!!
Start on | 2023-04-25 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2023-05-02
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
NOTE: This sprint is entirely OPTIONAL – no points will be lost if you ignore it
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84